## Agile Product Backlog
AGILE PRODUCT BACKLOG
USER STORY ID | As a <type of user> | I want to <perform some task> | so that I can <achieve some goal> | Value added to Project (1-10) | Priority | Acceptance Criteria
1 | Project Owner | Complete base game (everyone) | Have a base game to build off of | 10 | must have | 1: no softlocks 2: completed environment
2 | Project Owner | Scoring system (SM) | Scoreboard that tracks kills and accuracy and displays on screen | 5 | should have | 1: Keeps track of kill count 2: Tracks accuracy % 3: Displays on screen
4 | Project Owner | Minotaur Boss (KL) | AI Minotaur seeks out the player and kills them on contact | 7 | must have | 1:AI seeks out the player 2:AI successfully kills player 3: player should be able to kill minotaur
5 | Project Owner | Create a new map design (PW) | Setup a game environement | 10 | must have | 1: Completed environment 2: No light bleeding 3: No softlocks
6 | Project Owner | Secondary fire (AQ) | Set alternative fire mode to a flamethrower | 5 | nice to have | 1: successfully fires 2: successfully damages enemy